## Time Period 1
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 18/01/2022 - 01/02/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Abhishek Raj Meru | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Presentation | Gantt Chart Preparation | 18/01/2022 | 25/01/2022 | 1 | 0 | 10 | 10 | 0 | 0 | 21
2 | Presentation | Costing | 18/01/2022 | 25/01/2022 | 1 | 2 | 0 | 0 | 10 | 10 | 21
3 | Presentation | First Presentation | 18/01/2022 | 25/01/2022 | 8 | 10 | 0 | 0 | 0 | 0 | 18
4 | Control System Design | Control algorithms, code and equations | 25/01/2022 | 2022-01-02 | 2 | 0 | 0 | 0 | 20 | 18 | 40
5 | Simulation Devlopment | Static Simulation of robot, field, goal post and ball | 18/01/2022 | 2022-01-02 | 2 | 16 | 16 | 0 | 0 | 0 | 34
6 | Mathematical Model | Mathematical model research | 25/01/2022 | 2022-01-02 | 8 | 0 | 0 | 20 | 0 | 0 | 28
7 | System inputs and outputs | Research different types of inputs and outputs | 18/01/2022 | 25/01/2022 | 6 | 0 | 0 | 0 | 0 | 0 | 6
8 | Report | Report specification and research | 25/01/2022 | 2022-01-02 | 4 | 0 | 0 | 0 | 0 | 0 | 4
9 | Meetings | Discussions and reviews |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
10 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 34 | 30 | 28 | 32 | 32 | 30 | 184

## Time Period 2
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 01/02/2022 - 15/02/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Abhishek Raj | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team Member 5 | Hours: Team member 6 | Total hours
1 | Navigation Sensor Representation | Ball Design, Image Processing Algorithms | 2022-01-02 | 15/2/2022 | 0 | 0 | 0 | 0 | 25 | 9 | 34
2 | Control System Design | NAO6 Robot control system | 2022-01-02 | 15/2/2022 | 0 | 0 | 0 | 0 | 0 | 14 | 14
3 | Simulation Development | 2D Pitch Simulation | 2022-01-02 | 15/2/2022 | 12 | 18 | 0 | 0 | 0 | 0 | 30
4 | Environment Conditions | Ball Physics and Kicks | 2022-01-02 | 15/2/2022 | 0 | 0 | 23 | 21 | 0 | 0 | 44
5 | Behavioural Algorithm | Algorithm design on pen and paper | 2022-01-02 | 15/2/2022 | 9 | 6 | 0 | 0 | 0 | 0 | 15
6 | Team Meetings | Discussions and brainstorming | 2022-01-02 | 15/2/2022 | 8 | 8 | 8 | 8 | 8 | 8 | 48
7 | [10 empty] | 0
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 29 | 32 | 31 | 29 | 33 | 31 | 185

## Time Period 3
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 15/02/2022 - 01/03/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Raj Abhishek Meru | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Control Guidance | Robot Dynamics and Motion | 2/14/2022 | 2/28/2022 | 0 | 0 | 0 | 0 | 10 | 22 | 32
2 | Simulation Development | Pitch Simulation | 2/14/2022 | 2/28/2022 | 25 | 17 | 0 | 0 | 0 | 0 | 42
3 | Ball Dynamics | Ball Physics and Simulation on Pitch | 2/14/2022 | 2/28/2022 | 0 | 0 | 30 | 0 | 0 | 0 | 30
4 | Integration Research | Stateflow and Integration | 2/14/2022 | 2/28/2022 | 0 | 15 | 0 | 27 | 0 | 0 | 42
5 | Environment Visualization | Robot Spawning on Pitch | 2/14/2022 | 2/28/2022 | 0 | 0 | 0 | 0 | 24 | 10 | 34
6 | Team meetings | Discussions and brainstorming | 2/14/2022 | 2/28/2022 | 8 | 8 | 8 | 8 | 8 | 8 | 48
7 | [10 empty] | 0
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 33 | 40 | 38 | 35 | 42 | 40 | 228

## Time Period 4
Fortnightly Time Allocation Record
| Team Number: | Reporting Period:
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Yenuo Liu | 2706420L | Developer
| Team Member 5 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
1 | [9 empty] | 0
2 | [9 empty] | 0
3 | [9 empty] | 0
4 | [9 empty] | 0
5 | [9 empty] | 0
6 | [9 empty] | 0
7 | [9 empty] | 0
8 | [9 empty] | 0
9 | [9 empty] | 0
10 | [9 empty] | 0
11 | [9 empty] | 0
12 | [9 empty] | 0
13 | [9 empty] | 0
14 | [9 empty] | 0
15 | [9 empty] | 0
|  | OVERALL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Time Period 5
Fortnightly Time Allocation Record
| Team Number: | Reporting Period:
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Yenuo Liu | 2706420L | Developer
| Team Member 5 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
1 | [9 empty] | 0
2 | [9 empty] | 0
3 | [9 empty] | 0
4 | [9 empty] | 0
5 | [9 empty] | 0
6 | [9 empty] | 0
7 | [9 empty] | 0
8 | [9 empty] | 0
9 | [9 empty] | 0
10 | [9 empty] | 0
11 | [9 empty] | 0
12 | [9 empty] | 0
13 | [9 empty] | 0
14 | [9 empty] | 0
15 | [9 empty] | 0
|  | OVERALL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Time Period 6
Fortnightly Time Allocation Record
| Team Number: | Reporting Period:
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Yenuo Liu | 2706420L | Developer
| Team Member 5 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
1 | [9 empty] | 0
2 | [9 empty] | 0
3 | [9 empty] | 0
4 | [9 empty] | 0
5 | [9 empty] | 0
6 | [9 empty] | 0
7 | [9 empty] | 0
8 | [9 empty] | 0
9 | [9 empty] | 0
10 | [9 empty] | 0
11 | [9 empty] | 0
12 | [9 empty] | 0
13 | [9 empty] | 0
14 | [9 empty] | 0
15 | [9 empty] | 0
|  | OVERALL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0

## FInal Total
Total Time Allocation Record
Team Number:
| Name | Student # | Role
Team Member 1 | Anmol Kumar | 2709898K | Manager
Team Member 2 | Sarthak Ahuja | 2707209A | Developer
Team Member 3 | Jia Wei Tan | 2705295T | Developer
Team Member 4 | Yenuo Liu | 2706420L | Developer
Team Member 5 | Chaoyu Li | 2707728L | Developer
|  | Time Period | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
|  | 1 | 34 | 30 | 28 | 32 | 30 | 90
|  | 2 | 29 | 32 | 31 | 29 | 31 | 91
|  | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | 0 | 0 | 0 | 0 | 0 | 0
| OVERALL TOTAL |  | 63 | 62 | 59 | 61 | 61 | 181