## Time Period 1
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 18/01/2022 - 01/02/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Abhishek Raj Meru | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Presentation | Gantt Chart Preparation | 18/01/2022 | 25/01/2022 | 1 | 0 | 10 | 10 | 0 | 0 | 21
2 | Presentation | Costing | 18/01/2022 | 25/01/2022 | 1 | 2 | 0 | 0 | 10 | 10 | 21
3 | Presentation | First Presentation | 18/01/2022 | 25/01/2022 | 8 | 10 | 0 | 0 | 0 | 0 | 18
4 | Control System Design | Control algorithms, code and equations | 25/01/2022 | 2022-01-02 | 2 | 0 | 0 | 0 | 20 | 18 | 40
5 | Simulation Devlopment | Static Simulation of robot, field, goal post and ball | 18/01/2022 | 2022-01-02 | 2 | 16 | 16 | 0 | 0 | 0 | 34
6 | Mathematical Model | Mathematical model research | 25/01/2022 | 2022-01-02 | 8 | 0 | 0 | 20 | 0 | 0 | 28
7 | System inputs and outputs | Research different types of inputs and outputs | 18/01/2022 | 25/01/2022 | 6 | 0 | 0 | 0 | 0 | 0 | 6
8 | Report | Report specification and research | 25/01/2022 | 2022-01-02 | 4 | 0 | 0 | 0 | 0 | 0 | 4
9 | Meetings | Discussions and reviews |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
10 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 34 | 30 | 28 | 32 | 32 | 30 | 184

## Time Period 2
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 01/02/2022 - 15/02/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Abhishek Raj | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team Member 5 | Hours: Team member 6 | Total hours
1 | Navigation Sensor Representation | Ball Design, Image Processing Algorithms | 2022-01-02 | 15/2/2022 | 0 | 0 | 0 | 0 | 25 | 9 | 34
2 | Control System Design | NAO6 Robot control system | 2022-01-02 | 15/2/2022 | 0 | 0 | 0 | 0 | 0 | 14 | 14
3 | Simulation Development | 2D Pitch Simulation | 2022-01-02 | 15/2/2022 | 12 | 18 | 0 | 0 | 0 | 0 | 30
4 | Environment Conditions | Ball Physics and Kicks | 2022-01-02 | 15/2/2022 | 0 | 0 | 23 | 21 | 0 | 0 | 44
5 | Behavioural Algorithm | Algorithm design on pen and paper | 2022-01-02 | 15/2/2022 | 9 | 6 | 0 | 0 | 0 | 0 | 15
6 | Team Meetings | Discussions and brainstorming | 2022-01-02 | 15/2/2022 | 8 | 8 | 8 | 8 | 8 | 8 | 48
7 | [10 empty] | 0
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 29 | 32 | 31 | 29 | 33 | 31 | 185

## Time Period 3
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 15/02/2022 - 28/02/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Raj Abhishek Meru | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Control Guidance | Robot Dynamics and Motion | 2/14/2022 | 2/28/2022 | 0 | 0 | 0 | 0 | 10 | 22 | 32
2 | Simulation Development | Pitch Simulation | 2/14/2022 | 2/28/2022 | 25 | 17 | 0 | 0 | 0 | 0 | 42
3 | Ball Dynamics | Ball Physics and Simulation on Pitch | 2/14/2022 | 2/28/2022 | 0 | 0 | 30 | 0 | 0 | 0 | 30
4 | Integration Research | Stateflow and Integration | 2/14/2022 | 2/28/2022 | 0 | 15 | 0 | 27 | 0 | 0 | 42
5 | Environment Visualization | Robot Spawning on Pitch | 2/14/2022 | 2/28/2022 | 0 | 0 | 0 | 0 | 24 | 10 | 34
6 | Team meetings | Discussions and brainstorming | 2/14/2022 | 2/28/2022 | 8 | 8 | 8 | 8 | 8 | 8 | 48
7 | [10 empty] | 0
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 33 | 40 | 38 | 35 | 42 | 40 | 228

## Time Period 4
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 28/02/2022 - 15/03/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Raj Abhishek Meru | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
1 | Control Guidance | Robot Dynamics and 3D Modeling | 2/28/2022 | 3/15/2022 | 0 | 0 | 0 | 0 | 0 | 27 | 27
2 | Simulation Development | Visualization | 2/28/2022 | 3/15/2022 | 0 | 0 | 26 | 0 | 15 | 0 | 41
3 | Ball Dynamics | Ball Physics and Dynamics | 2/28/2022 | 3/15/2022 | 0 | 0 | 0 | 24 | 0 | 0 | 24
4 | Integration Research | Stateflow and Integration | 2/28/2022 | 3/15/2022 | 0 | 25 | 0 | 0 | 0 | 0 | 25
5 | Algorithm Development | Attacker, Defender and Goalkeeper Algorithms | 2/28/2022 | 3/15/2022 | 23 | 0 | 0 | 0 | 0 | 0 | 23
6 | Environment Visualization | Game Controller | 2/28/2022 | 3/15/2022 | 0 | 0 | 0 | 0 | 11 | 0 | 11
7 | Team meetings | Discussions and brainstorming | 2/28/2022 | 3/15/2022 | 8 | 8 | 8 | 8 | 8 | 8 | 48
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
16 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 31 | 33 | 34 | 32 | 34 | 35 | 199

## Time Period 5
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: 16/03/2022 - 29/03/2022
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Raj Abhishek Meru | 2709585M | Developer
| Team Member 5 | Yenuo Liu | 2706420L | Developer
| Team Member 6 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
1 | Control Guidance and Modeling | Robot Dynamics and 3D Modeling | 3/16/2022 | 3/29/2022 | 0 | 0 | 0 | 0 | 0 | 28 | 28
2 | Simulation Development | Simulation and Visualization | 3/16/2022 | 3/29/2022 | 0 | 0 | 0 | 0 | 18 | 0 | 18
3 | Ball Dynamics | Ball Physics and Dynamics | 3/16/2022 | 3/29/2022 | 0 | 0 | 0 | 29 | 0 | 0 | 29
4 | Strategy Design | Strategy Development and Stateflow Integration | 3/16/2022 | 3/29/2022 | 0 | 30 | 0 | 0 | 0 | 0 | 30
5 | Algorithm Development | Goalkeeper Algorithm and Role Switching | 3/16/2022 | 3/29/2022 | 19 | 0 | 0 | 0 | 0 | 0 | 19
6 | Algorithm Development | Algorithm Inprovement | 3/16/2022 | 3/29/2022 | 0 | 0 | 0 | 0 | 14 | 0 | 14
7 | Environment Visualization | Ball and Pitch Visualization | 3/16/2022 | 3/29/2022 | 0 | 0 | 31 | 0 | 0 | 0 | 31
8 | Report | Report | 3/16/2022 | 3/29/2022 | 0 | 0 | 0 | 0 | 0 | 4 | 4
9 | Team meetings | Discussions and brainstorming | 3/16/2022 | 3/29/2022 | 8 | 13 | 13 | 13 | 13 | 13 | 73
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
16 | [10 empty] | 0
17 | [10 empty] | 0
18 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 27 | 43 | 44 | 42 | 45 | 45 | 246

## Time Period 6
Fortnightly Time Allocation Record
| Team Number: | Reporting Period:
|  | Name | Student # | Role
| Team Member 1 | Anmol Kumar | 2709898K | Manager
| Team Member 2 | Sarthak Ahuja | 2707209A | Developer
| Team Member 3 | Jia Wei Tan | 2705295T | Developer
| Team Member 4 | Yenuo Liu | 2706420L | Developer
| Team Member 5 | Chaoyu Li | 2707728L | Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
1 | [9 empty] | 0
2 | [9 empty] | 0
3 | [9 empty] | 0
4 | [9 empty] | 0
5 | [9 empty] | 0
6 | [9 empty] | 0
7 | [9 empty] | 0
8 | [9 empty] | 0
9 | [9 empty] | 0
10 | [9 empty] | 0
11 | [9 empty] | 0
12 | [9 empty] | 0
13 | [9 empty] | 0
14 | [9 empty] | 0
15 | [9 empty] | 0
|  | OVERALL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0

## FInal Total
Total Time Allocation Record
Team Number:
| Name | Student # | Role
Team Member 1 | Anmol Kumar | 2709898K | Manager
Team Member 2 | Sarthak Ahuja | 2707209A | Developer
Team Member 3 | Jia Wei Tan | 2705295T | Developer
Team Member 4 | Yenuo Liu | 2706420L | Developer
Team Member 5 | Chaoyu Li | 2707728L | Developer
|  | Time Period | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Total hours
|  | 1 | 34 | 30 | 28 | 32 | 30 | 90
|  | 2 | 29 | 32 | 31 | 29 | 31 | 91
|  | 3 | [5 empty] | 0
|  | 4 | 27 | 43 | 42 | 45 | 45 | 132
|  | 5 | [5 empty] | 0
| OVERALL TOTAL |  | 90 | 105 | 101 | 106 | 106 | 313